ARPA – Projects, Decisions Needed, and Timeline

KEY

Orange = Need to hear back from consultant on whether it is an allowable expense.

Green = Consensus for moving forward towards approval.

Blue = Consensus reached but vote at legislative session needed.

| Spending Category | Consensus on Any Project? | Cost | Decisions/Information Needed | Dates for Decisions | Owners and Helpers | Community Outreach |
| --- | --- | --- | --- | --- | --- | --- |
| Stormwater Management | Perry Street - 33rd and Perry - 31st and Perry - 31st Street Alley | 33rd and Perry project incorporated into the 3300 block of RIA/Perry Street cost estimate in government services bucket. $79k ($609k total cost; $530k received from state through state’s FY23 budget) $84k for 31st Street Alley | - 33rd and Perry – cost estimate needed to be included in larger 3300 block RIA project to supplement already allocated funding. - 31st and Perry – need to have LID/Ecosite examine potential to create green space across Perry Street that would prevent traffic from coming into Mount Rainier off Eastern Avenue and capture all stormwater off Eastern Avenue. - 31st Street Alley – need to have discussion with developer on their project and partner to rehab alleyway. |  | Kamali LID Ecosite Chesek | Jarrett and Luke meeting at 31st and Perry with nearby residents Celina and Luke also met with stormwater management consultants and a few residents |
|  | Arundel Road – Extension of County’s Green Street | $2.39m | - Need to have discussion with County to see if they could use County money to extend project to Eastern Avenue or what a partnership may look like cost-wise. |  | Kamali LID Ecosite Chesek | Toole Design recommendation |
|  | 32nd Street (Btw Shephard and Taylor) | $458k (Option 1 – concrete sidewalks) $520k (Option 2 – permeable sidewalks) |  |  |  | Email discussion w/residents regarding complaints dating back two years |
|  | 31st Street Green Street (Btw Arundel and Windom Road) | $332k (Option 1 - concrete sidewalks) $374k (Option 2 – permeable sidewalks) |  |  | Kamali LID Ecosite Chesek |  |
|  | Southside redesign of 35th/36th/37th | $1.12m | - Need to have community meeting with southside residents. - Need traffic study |  | Kamali LID Ecosite Chesek | Celina and Luke meet-up at 37th Street Park |
|  | Newton Street from 34th to 37th Streets | $922k (Option 1 - permeable gutter whole street) | - Need cost estimate from LID/Ecosite (meeting scheduled for 11/5/21). - Estimates received. - Will be added to weekly reports after 10.17.22. |  | Kamali LID Ecosite Chesek | Several reported residential issues Celina and Luke visited site with stormwater consultants and two residents |
|  | Spatial Analysis of Tree Canopy | $10k | - Tree Commission needed to present |  | Kamali LID Ecosite Chesek | Tree Commission recommendation (Tree Commission found free resource) |
|  | Climate resilience and Stormwater Mitigation Urban Tree Planting | $20k | - Tree Commission needed to present. - 10.17.22 – City Manager will follow up with Tree Commission to determine status. |  | Kamali LID Ecosite Chesek | Tree Commission recommendation |
|  | Mount Rainier Elementary Stormwater Project | $50-75k | - Reach out to County to get idea of their Capital Improvement Plan for the School District (Celina will reach out to Pamela Boozer). |  | Kamali Benitez | PTO recommendation |
|  | Joe’s Movement Emporium | $200k |  |  |  |  |
|  | Malinda Miles Building Green Roof | $231k |  |  |  |  |
| Education | Thomas Stone: - Expand outdoor classrooms - Math tutoring - Improve air filtration | $15-20k $8-10k $7.5-25k | - Expand outdoor classrooms: - Mayor informed school - Need concrete proposal with written justification as to benefit to Title 1 populations at school. - Math tutoring: - Need discussion with county on planned efforts (Celina will ask Pamela Boozer). - Improve air filtration: - Need discussion with county on planned efforts (Celina will ask Pamela Boozer). |  | Kamali Benitez | PTO recommendation |
|  | Mount Rainier Elementary School - Expand outdoor classrooms - Improve air filtration | $20k $7.5-25k | - Expand outdoor classrooms: - Mayor informed school. - Need concrete proposal with written justification as to benefit to Title 1 populations at school. - Math tutoring: - Need discussion with county on planned efforts (Celina will ask Pamela Boozer). - Improve air filtration: - Need discussion with county on planned efforts (Celina will ask Pamela Boozer). |  | Kamali Benitez | PTO recommendation |
|  | Access to Public Resources for Hispanic or Latino Populations | $50k Additional allocation of $36,000 on 6/6/23 Total of $86,000 | - Potential programs it could fund: - Literacy through Arts Education - Arte Para Todos - Will have to build process for submitting documentation (dependent on administrative steps taken). - Consultant will work with Kamali on grant process. - Notice of funding availability ready on 2.9.22. - Have received three proposals as of 3.15. - Awarded money to Joe’s Movement Emporium on 5.13.22. |  | Kamali Tarlau |  |
|  | Early childhood vouchers for daycare or after-school programming |  | - Could do child assistance program for residents with unemployed family members or target families negatively impacted by COVID. |  | Kamali Benitez |  |
|  | 529 College Savings Accounts for elementary students on free or reduced lunch | $1-2m | - Need to hear back from consultant on whether this is an allowable expense. - Does not meet eligibility standard because of time period for benefit to the students. |  | Kamali Chesek |  |
| Business Aid | Small Business Assistance Grant Program (up to $5,000 to replace loss revenue for city businesses) | $50k Added $20k for $70k total | - Originally, this was an MRBA proposal, but it will be administered by the City. - Need to create administrative process for granting money. - Consultant will provide City Manager with guidance on for grant application. - Application is ready as of 2.8.22. - Have received 10 applications from small businesses; decisions made on 3 to give full $5k. Reviewing 6 more as of 3/1/22. - No applications received from non-profits as of 3/1/22. - As of 3/15, 17 applications received (5 need more information; awarded 7 applicants; denied 2). - Awarded 10 businesses in spring 2022. - Two more businesses are awaiting approval; in which case, may increase by $20k. - Increased by $20k in 06/22. - Full $20k awarded. |  | Kamali Tarlau | MRBA recommendation |
|  | Partnership with FSC for Investments (e.g., façade improvements, equipment upgrades) |  | - Someone needs to develop a proposal for consideration and see what County is providing to avoid redundancy. |  | Kamali Chesek |  |
| Residential Aid | Wifi |  |  |  |  |  |
|  | Food Security | $100k (first round) $200k (second round) $300k total | - Thanksgiving and holiday baskets qualified. - Will continue to run programs in-house. - Report of assistance will be provided to Council. - Potential for more funding; potential for third party partnerships. - Food distribution includes to Rainier Manor. - Progress continues for Thanksgiving baskets as of 10.17.22. |  | Kamali Benitez |  |
|  | Rental relief (utilities, back rent) *potential to provide legal assistance as well as a later date | $55k Added $5k on 2.28.23 | - Need to develop a proposal for consideration and see what County is providing to avoid redundancy. - Initial offering will be for $1,000 maximum and focus on back rent or utilities. Checks will be cut to landlord or utility. - Tenant or landlord may apply. - Will cross check with County applicants to ensure no double dipping. - Draft applications are almost ready and pending Mayor/Council review. - Application review process underway; $18k awarded as of 10.17.22. |  | Kamali Benitez |  |
|  | Cash incentive |  | - Need to develop a proposal for consideration and see what County is providing to avoid redundancy. |  |  |  |
|  | Workforce development (laptop/CDL/career training) |  | - Need to develop a proposal for consideration and see what County is providing to avoid redundancy. |  |  |  |
| City-Owned Parks or Property | Richardson Park | $150k | - Cost estimate for equipment and fencing. - $106k has been placed in the Governor’s budget for Richardson Park. If approved, this cost will go down to $44k - Increase in costs means initial allocation proper | Need to allocate at Dec. 7 leg. Session. | Kamali Benitez | Complaints received for updating equipment. Serves largest population of city. |
|  | Spring Park | 11k stormwater fix Already allocated $50k from grant funding for park redesign | - Jack Sullivan provided latest drawings; need to send out RFP. - Reached out to County to connect well to inlet at Shepherd and 33rd. - Project needs to start in the spring to take advantage of grant money. | Need cost estimate to ensure money allocated. Need to start work in spring 2022 | Kamali Stolttzfus | Multiple community meetings held on project. Project is in partnership with Little Friends for Peace (LFFP). |
|  | Rogers Park |  | - Jarrett reached out to interested residents in restarting conversation to develop park design. - Need a cost estimate for rejuvenation. |  | Kamali Stolttzfus | Community meeting held in 2020 and will be scheduled. |
|  | Edgemont Park |  | - Might be incorporated into 31st and Perry stormwater retrofits. - Residents have proposed small garden bed in park. |  | Kamali Stolttzfus |  |
| Healthcare | Social worker | $120k ($40k annually for three years of ARPA permitted expenses) | - Could expand part-time social worker into full-time social worker. - Next step would be to create budget amendment to approve. | Need to allocate at Dec. 7 leg session | Kamali Benitez |  |
|  | Crisis management |  |  |  |  |  |
|  | Health outreach |  | - Need to develop proposal. Potential for partnerships. |  |  |  |
|  | Vaccine incentives | $10k | - Neighboring Gateway municipalities giving $25 gift certificates. - Mayor reaching out to municipalities, County Councilperson Taveras’ office, and schools on potential partnerships. | Need to allocate at Dec. 7 leg session |  |  |
|  | Workshops on domestic violence, substance abuse, COVID-stress |  | - Need to develop proposal. Potential for partnerships. |  |  |  |
| City – ARPA Related Administration Expenses and COVID-19 Mitigation | Reimburse City for COVID-19 Loss |  | - Need to wait for new finance director? |  | Kamali Finance Himmler |  |
|  | Bonuses for front-line workers and/or hazard pay, including back pay bonuses, for those employees who have consistent face-to-face interaction with the public. | $262k | - Mayor requested proposal on hazard pay from City Manager. - Awarded |  | Kamali Finance Himmler |  |
|  | Program Manager | $200k (may lower as position continues to remain unfilled; was originally approved for $300k) | - Job description finished. - Position was posted online on 11.17.21. - Program manager will help build out administrative process for grantees. - As of 12.21.21, still considering candidates. - As of 5.17.22, City Manager believes may be able to run in-house. - As of 5.1.23, only done in-house; could remove allocation |  | Kamali |  |
|  | ARPA Consultant | $100k total ($30 per year with contingency of $10k in case assistance needed w/projects after three years) | - Approved and contracted with Thomas Michael LLC. - 10/22 – in process of renewing contract (no increase in price). - Contract needs to be renewed on an annual basis (voted to renew on 11/1/22). - We may need to add extra funding for FY25 and 26 when funds are still being spent |  |  |  |
| Government Services | The 3300 Block of Rhode Island Avenue and the 3300 Block of Perry Street, including stormwater fixes at 33rd and Perry and Memorial Park | $1m | - Final cost estimate is $1.4 million. - With $400k already allocated ($300k from grant funding), the city need only $1m from ARPA funding. - Could be allocated through the “Government Services” bucket. - If approved, need to continue to apply for funding for other items. - As of 5/19/22, LID is working on permit applications; working out issue with Park and Planning. - Permit approved with Park and Planning and SHA, and will be submitted to DPIE. | Kamali Chesek |  |  |
|  | Potts Hall Welcome Center | $1 million | - After final Treasury guidance given, could be considered an appropriate expense. - $250k allocated from FY23 state budget; $1.3 million proposed for FY24 state budget. - Four bids received that are being reviewed by the architects. Lowest bid was $5.9m; City Manager will present us with proposal for moving forward. | Kamali |  |  |
|  | 3409 Rhode Island Avenue | $45k | - Proposal to upgrade the second floor of Rhode Island Avenue to be able to rent out space to produce revenue. - First floor was already renovated and holds Code Compliance. - Project completed with caveat of ADA compliant build out required if we want to host a business (residential rental permitted as is). | Kamali |  |  |
|  | Malinda Miles Building | $150k (completed project is over budget) | - Current cost projection to make building habitable. - Construction began on 5.16.22 (4-6 weeks until completion) - Project completed |  |  |  |
|  | Scholarships for Students | $63k (21k annually for three years of ARPA spending) $42,000 (added on 5/1) Total = $105,000 | - Will buttress existing City expense on scholarships. - On April 2, will present calendar of scholarship process. - As of 4/29, applications are out and review period will start soon. - Awarded 7 scholarships at $3k each in June 2022. - Orientation for 2023 scholarship committee planned. | Kamali Benitez |  |  |
|  | Bike Co-Op Window Replacement and Rear Shelter Replacement | $16k | - Need to hear back from consultant on whether this is an allowable expense. - Because it is a city building, trying to see if there was any lost revenue at Bike Co-Op during pandemic. - Recipients of revenue loss can take a standard allowance; but, if the City is spending it on a typical “governmental service,” it is also an allowable expense (i.e., if this is what the city would have done without ARPA funding, it’s an allowable expense.) - Determined it’s an allowable expense. - Approved on 11/1. | Kamali Benitez |  |  |
|  | Gateway CDC Proposal to Subsidize Artist Space in the Gateway Arts District | $125,000 | - Presentation given at 6.21.22 work session. |  |  |  |
|  | Operation Arts Project | $5,000 | - Public arts project similar to little library program, allowing residents to create and leave art in built structure in town. - Met with Arts Commission and will submit contract to City/Legal. |  |  |  |
|  | Police Computers | $55,000 | - Funding allocated 5/1 |  |  |  |
|  | Police Uniforms | $36,500 |  |  |  |  |
|  | Bike Co-Op | $4,000 |  |  |  |  |
|  | Streets and Sidewalks | $100,000 |  |  |  |  |
|  | Throne Bathroom | $30,000 |  |  |  |  |
|  | City-Based Home Repair Program | $150,000 | - Need to develop a proposal for consideration and see what County is providing to avoid redundancy. - Valerie working on proposal - Funding allocated on 5/1 - Accepting proposals and money going out as of January 2024 |  | Valerie |  |
| Total Allocated (actual spending may be different) |  | $5,114,500 |  |  |  |  |
| Remaining funds |  | $315,500 |  |  |  |  |
| Potential additional allocated |  |  |  |  |  |  |
| Potential Remaining |  |  |  |  |  |  |